## All Areas
Pot Hole Action Fund report
Schemes delivered in 2017 / 18 using the pot hole action funding which were not previously programmed for 2017 / 18.
Allerdale 17/18 Programme:
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
U2984 | Allerdale | Brierydale Lane Stainburn | Carriageway | Resurfacing | 2017-11-13 | 2017-11-17 | 23059.7
U2623 | Allerdale | Robinson Street Workington | Carriageway | Resurfacing | 2017-11-20 | 2017-11-21 | 6243.7
U2493 | Allerdale | Duke Street, Workington | Carriageway | Resurfacing | 2017-11-21 | 2017-11-23 | 8956
U2081 | Allerdale | Fitz Farm | Carriageway | Resurfacing | 2017-11-24 | 2017-11-24 | 4259.5
U7041 | Allerdale | Kelsick Park Junction, Seaton | Carriageway | Resurfacing | 2017-11-27 | 2017-11-27 | 4414.34
U2803 | Allerdale | James Street, Maryport | Carriageway | Resurfacing | 2017-11-28 | 2017-11-30 | 11095
U2754 | Allerdale | Brookside, Maryport | Carriageway | Resurfacing | 2017-12-01 | 2017-12-01 | 3067
U2738&U2781 | Allerdale | Alne Road and Edinburgh Road, Maryport | Carriageway | Resurfacing | 2017-12-04 | 2017-12-12 | 17422
| Allerdale | Edinburgh Road, Maryport | Carriageway | Resurfacting | 2017-12-11 | 2017-12-12 | 6667.68
U2782 | Allerdale | Ennerdale Road, Maryport | Carriageway | Resurfacing | 2017-12-19 | 2017-12-21 | 10045.92
U2322 | Allerdale | Main Street Dearham | Carriageway | Resurfacing | 2018-01-08 | 2018-01-09 | 8910.25
C2001 | Allerdale | Midtown Dearham | Carriageway | Resurfacing | 2018-01-10 | 2018-01-10 | 3125.2
U2292 | Allerdale | Croft Cresent, Dearham | Carriageway | Resurfacing | 2018-01-11 | 2018-01-12 | 11102.97
U2294 | Allerdale | Browside Road Dearham | Carriageway | Resurfacing | 2018-01-15 | 2018-01-16 | 3890.85
U2226 | Allerdale | Crooklety Bridge to Millbeck | Carriageway | Resurfacing | 2018-01-17 | 2018-01-19 | 33193.15
B5302 | Allerdale | Abbeytown to Silloth | Carriageway | Resurfacing | 2018-02-19 | 2018-03-08 | 128247.86
C2064 | Allerdale | Cockermouth to Embleton | Carriageway | Resurfacing | 2018-01-12 | 2018-01-15 | 16007.32
C2003 | Allerdale | A594 to Tallentire | Carriageway | Resurfacing | 2018-03-16 | 2018-03-16 | 14838.52
C2003 | Allerdale | Outside Greenside Tallentire Village | Carriageway | Resurfacing | 2018-03-19 | 2018-03-19 | 3604
U2093 | Allerdale | Bridekirk to Tallentire Village | Carriageway | Resurfacing | 2018-03-20 | 2018-03-21 | 12602
U2112 | Allerdale | New Park reby | Carriageway | Resurfacing | 2018-03-22 | 2018-03-22 | 3912.3
U2203 | Allerdale | Hundith Hill | Carriageway | Resurfacing | 2018-03-23 | 2018-03-23 | 15373.89
U2234 | Allerdale | Dale Bottom Keswick | Carriageway | Resurfacing | 2018-03-26 | 2018-03-29 | 40193
B5302 | Allerdale | Wigton Road Silloth | Carriageway | Resurfacing | 2018-03-29 | 2018-03-29 | 3557
| Allerdale | Ruthwaite | Carriageway | Resurfacing | 2018-02-21 | 2018-02-21 | 3500
| Allerdale | Materials |  |  |  |  | 1694.65
| Allerdale | Staff Time |  |  |  |  | 10457.21
[6 empty] | Total | 409441.01
Barrow 17/18 Programme:
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
| Barrow | Greengate Street, Barrow | Carriageway | Carriageway Patching | 2017-04-01 | 2017-04-01 | 6787.88
U6177 | Barrow | Duke Street Roundabout | Carriageway | Carriageway Patching | 2018-03-08 | 2018-03-14 | 9796.22
C6007 | Barrow | Central Drive | Carriageway | Carriageway Patching | 2018-01-10 | 2018-01-11 | 2574.46
U6236 | Barrow | Southampton Street | Carriageway | Carriageway Patching | 2018-01-03 | 2018-01-09 | 11703.76
U6241 | Barrow | Strathnaver Ave | Carriageway | Carriageway Patching | 2018-01-23 | 2018-02-01 | 20700.77
U6235 | Barrow | Bristol Street | Carriageway | Carriageway Patching | 2018-01-12 | 2018-01-22 | 13418.45
U6240 | Barrow | Empress Drive | Carriageway | Carriageway Patching | 2018-02-02 | 2018-02-09 | 8959.91
U6238 | Barrow | Mikasa Street | Carriageway | Carriageway Patching | 2018-02-12 | 2018-02-15 | 3791
U6234 | Barrow | Euryalus Street | Carriageway | Carriageway Patching | 2018-02-15 | 2018-02-19 | 6782.74
U6235 | Barrow | Church Lane, Walney | Carriageway | Carriageway Patching | 2018-02-20 | 2018-03-07 | 25975.37
U6162 | Barrow | Abbotsvale | Carriageway | Carriageway Patching | 2018-03-14 | 2018-03-22 | 14958.49
| Barrow | Materials - Instaband |  |  |  |  | 6048
| Barrow | Staff Time |  |  |  |  | 13442.14
[6 empty] | Total | 144939.19 | 144939.19
Carlisle
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
C1027 | Carlisle | Murray Holme | Carriageway | Pot Hole Repairs | 2017-11-20 | 2017-11-24 | 42515.75
Various | Carlisle | Carlisle Works Package (Eastern Way, Durdar Xrds, Henderson Road, Kingmoor Road | Carriageway | Pot Hole Repairs | 2018-01-22 | 2018-01-26 | 43638.99
C1016 | Carlisle | Westlinton to Floriston | Carriageway | Pot Hole Repairs | 2018-01-22 | 2018-01-26 | 39914.21
C2042 | Carlisle | Burgh Road area | Carriageway | Pot Hole Repairs | 2018-02-19 | 2018-02-24 | 43363.83
Various | Carlisle | Highbridge and Clesskets | Carriageway | Pot Hole Repairs | 2018-03-22 | 2018-03-23 | 30949.73
Various | Carlisle | Joblin Purser Concrete road repairs. (Arnside Road) (Beechwood)(Stonegarth)Carlisle (Dacre Road Brampton) | Carriageway | Pot Hole Repairs | 2018-03-12 | 2018-03-30 | 49000
U1170 | Carlisle | Tarraby | Carriageway | Pot Hole Repairs | 2018-02-19 | 2018-02-23 | 24870.57
| Carlisle | A Plant | EP00299216 | Temp TM |  |  | 6346.5
| Carlisle | Cumberland News | Advertising |  |  |  | 1214.4
|  | Staff Time |  |  |  |  | 25509.62
[6 empty] | Total | 307323.6
Copeland 17/18 Programme:
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
B5306 | COPELAND | Howgate to Distington | Carriageway | Patching | 2018-02-15 | 2018-02-20 | 16937
A5086 | COPELAND | A5086 Frizington Road | Carriageway | Pothole Repairs/Patching | 2018-02-15 | 2018-02-19 | 12632.75
A595 | COPELAND | A595 Buckman Brow | Carriageway | Pothole Repairs/Patching | 2018-03-19 | 2018-03-24 | 57257.25
U4011 | COPELAND | Victoria Road, Whitehaven | Carriageway | Patching | 2018-02-21 | 2018-02-21 | 3576.55
| COPELAND | Common End to Boonwood | Carriageway | Patching | 2018-03-26 | 2018-03-26 | 5474
U4292 | COPELAND | The Square, Bransty | Carriageway | Patching | 2018-02-12 | 2018-02-16 | 5000
U4471 | COPELAND | Studfold, Pica | Carriageway | Pothole Repairs | 2018-02-19 | 2018-02-21 | 3600
| COPELAND | Burnmoor Avenue, Mirehouse | Carriageway | Patching | 2018-02-23 | 2018-02-23 | 4000
| COPELAND | Derwentwater Road, Mirehouse | Carriageway | Patching | 2018-02-19 | 2018-02-23 | 15000
U4247 | COPELAND | Briscoe Mount | Carriageway | Patching | 2018-03-19 | 2018-03-23 | 8500
U4032 | COPELAND | Blackhowe Road | Carriageway | Pothole Repairs/Patching | 2018-03-26 | 2018-03-30 | 11000
U4263 | COPELAND | Sunnyside Egremont | Carriageway | Pothole Repairs/Patching | 2018-03-05 | 2018-03-09 | 9000
C4015 | COPELAND | BlackLing | Carriageway | Pothole Repairs/Patching | 2018-03-23 | 2018-03-23 | 2500
U4349 | COPELAND | West Row, Kells | Carriageway | Pothole Repairs/Patching | 2018-03-05 | 2018-03-07 | 10000
U4007 | COPELAND | Parton Brow | Carriageway | Pothole Repairs/Patching | 2018-01-22 | 2018-01-26 | 8895
U4375 | COPELAND | Newlands Avenue | Carriageway | Pothole Repairs/Patching | 2018-01-08 | 2018-01-11 | 16627.66
U4349 | COPELAND | Mid Street, Kells | Carriageway | Pothole Repairs/Patching | 2018-02-26 | 2018-03-02 | 8500
U4007 | COPELAND | Foundary Road, Parton | Carriageway | Pothole Repairs/Patching | 2018-01-22 | 2018-01-26 | 8000
| COPELAND | Staff Time |  |  |  |  | 17203.43
[6 empty] | Total | 223703.64
Eden 17/18 Programme:
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
A686 | Eden | Kemplay Bank Roundabout, Penirth A686 Slip Road Exit | Carriageway | Resurfacing | 2018-02-14 | 2018-02-14 | 18192.95
A686 | Eden | Meathaw Hill, Nr Alston | Carriageway | Resurfacing | 2018-03-05 | Ongoing | 83692.3
Various | Eden | Various Eden - Order HED02061 | Carriageway | Pothole Repairs | 2017-07-18 | 2017-09-22 | 29756.07
Vairous | Eden | Various Eden - Order HED02129 | Carriageway | Pothole Repairs | 2017-09-22 | 2017-12-12 | 29035.98
A686 |  | Meathaw Hill, Nr Alston HED02277 | Carriageway | Drainage | 2018-02-19 | 2018-03-12 | 9025.88
|  | Materials & Advertising |  |  |  |  | 8758.5
| Eden | Staff Time |  |  |  |  | 30079.59
[6 empty] | Total | 208541.27 | 208541.27
Barrow 17/18 Programme:
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
[6 empty] | Total | 0
South Lakeland 17/18 Programme:
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
[6 empty] | Total | 0
South Lakes 17/18 Pothole Fund Works
Scheme Name |  |  | Scheme Details |  | Works Start Date | Completion Date | Cost to CCC (£k)
Road No. | District | Name | Asset Groups | Scheme Type - eg, pothole repairs, resurfacing, patching
C6002 | South Lakes | Dendron | Carriageway | Resurfacing | 2017-04-03 | 2017-04-04 | 23440
U925 | South Lakes | Kentwood Road, Kendal | Carriageway | Resurfacing | 2017-05-19 | 2017-05-19 | 19789
U880 | South Lakes | Thornleigh Road, Kendal | Carriageway | Resurfacing | 2017-05-19 | 2017-05-19 | Part of Kentwood Road costs
B6254 | South Lakes | Nr Kearstwick | Carriageway | Resurfacing | 2017-07-06 | 2017-07-06 | 27712
C5085 | South Lakes | Biggins Road, Kirkby Lonsdale | Carriageway | Resurfacing | 2017-05-30 | 2017-05-31 | 38805
U782 | South Lakes | Skewbarrow, Kendal | Carriageway | Resurfacing | 2017-05-23 | 2017-05-23 | 14819
U5714 | South Lakes | Brogden Street, Ulverston | Carriageway | Resurfacing | 2017-04-09 | 2017-04-09 | 23203
U5712 | South Lakes | Lightburn Road, Ulverston | Carriageway | Resurfacing | 2017-04-13 | 2017-04-13 | 22325
Various | South Lakes | Long Meadows Lane, Halforth Farm, Underbarrow Road, Newby Bridge (The Swan) | Carriageway | Resurfacing | 2017-04-03 | 2017-04-06 | 73344
B5282 | South Lakes | Station Road, Arnside | Carriageway | Resurfacing | 2017-05-05 | 2017-05-05 | 44940
U5676 | South Lakes | Fernhill Road, Grange | Carriageway | Resurfacing | 2017-05-09 | 2017-05-09 | 37605
C5031 | South Lakes | Church Road, Little Urswick | Carriageway | Resurfacing | 2017-04-10 | 2017-04-12 | 64205
C5071 | South Lakes | Natland Village | Carriageway | Resurfacing | 2017-05-30 | 2017-06-01 | 93715
C5108 | South Lakes | Windermere Road, Staveley | Carriageway | Resurfacing | 2017-06-19 | 2017-06-22 | 86075
U837 | South Lakes | Peat Lane, Kendal | Carriageway | Resurfacing | 2017-06-16 | 2017-06-16 | 13643
U5365 | South Lakes | Gatebeck | Carriageway | Resurfacing | 2017-04-12 | 2017-04-12 | 30818
Various | South Lakes | Minor Carriageway Patching | Carriageway | Patching | Various | Various | 150000
A591 | South Lakes | Kendal Bypass | Carriageway | Patching | 2018-03-26 | 2018-03-27 | 29928
U5489 | South Lakes | Grizedale, Sedbergh | Carriageway | Resurfacing | 2018-03-16 | 2018-03-16 | 38358
Various | South Lakes | Staff Time |  |  | Various | Various | 3398
[6 empty] | Total | 836122

## Summary
Total Costs of all 6 Areas
Allerdale | 409441.01
Barrow | 144939.19
Carlisle | 307323.6
Copeland | 223703.64
Eden | 208541.27
South Lakes | 836122
Total | 2130070.71