## All Areas
Pot Hole Action Fund report
Schemes to be delivered in 2018 / 19 using the pot hole action funding
Allerdale
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
B5302 | Allerdale | Abbeytown to Silloth | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-04-25 | 2018-05-09 | 2018-04-30 | 2018-05-17 | 30000
B5299 | Allerdale | O/s Allhallows church | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-04-30 | 2018-05-01 | 2018-04-30 | 2018-05-23 | 140822
B5299 | Allerdale | Fletchertown Corner | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-04-30 | 2018-05-01 | 2018-04-30 | 2018-05-23 | 100603.47
B5299 | Allerdale | A595 mealsgate Junction | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-04-30 | 2018-05-01 | 2018-04-30 | 2018-05-23 | 49406.35
| Allerdale | Castle Lonning, Keswick | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-05-08 | 2018-05-14 | 2018-05-08 | 2018-05-19 | 11018.03
U2081 | Allerdale | Arkleby Hall to Fitz | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-10-22 | 2018-10-26 | 2018-11-19 | 2019-11-22 | 12701.73
C2041 | Allerdale | Caldbeck Crossroads | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-08-13 | 2018-08-14 | 2018-08-09 | 2018-08-16 | 3284.14
U2077 | Allerdale | A596 to Gowrie | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-01-28 | 2019-02-01 | 2018-11-19 | 2018-11-22 | 10647.84
U2081 | Allerdale | A595 to Blennerhasset | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-07-16 | 2018-07-27 | 2018-07-16 | 2018-07-27 | 20890.66
C2040 | Allerdale | Cross Lane Wigton | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-07-30 | 2018-08-03 | 2018-07-30 | 2018-08-03 | 7646.14
B5300 | Allerdale | Crosscannonby to Allonby | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-10-22 | 2018-10-26 | 2018-10-22 | 2018-10-24 | 7730.85
C2001 | Allerdale | Threapland to Bothel | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-08-20 | 2018-08-24 | 2018-10-22 | 2018-10-24 | 14722.67
C2051 | Allerdale | Wiggonby to Blackbrow | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-02-25 | 2019-03-08 | 2019-02-25 | 2019-03-08 | 23708.94
| Allerdale | Low Bank Farm Lorton | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-08-28 | 2018-09-03 | 2018-08-28 | 2018-08-31 | 4491.68
| Allerdale | Hollin Root to Burns Farm | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2018-09-10 | 2018-09-14 | 2018-09-10 | 2018-09-13 | 5781.99
C2027 | Allerdale | Hundith Hill | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-08-30 | 2018-08-31 | 2018-08-30 | 2018-08-31 | 39791.22
C2021 | Allerdale | Uldale to Aughtree | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Pothole Repairs | 3 - High | 2018-07-23 | 2018-07-31 | 2018-07-09 | 2018-07-13 | 7779.22
U2189 | Allerdale | Little Clifton | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-01 | 2018-08-30 | 2018-08-30 | 2000
U2188 | Allerdale | Mayfield Greysouthern | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-01 | 2018-08-03 | 2018-08-03 | 2500
A66T | Allerdale | Thornthwaite (Jet Patch) | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 2018-08-01 | 2018-08-03 | 2018-08-01 | 2018-08-01 | 4000
B5289 | Allerdale | Buttermere (Jet Patch) | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-03 | 2018-07-30 | 2018-07-31 | 9000
U2224 | Allerdale | Stair to Skelgill (Jet Patch) | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-03 | 2018-08-02 | 2018-08-02 | 3000
U2060 | Allerdale | Knoxwood to Hardcake (Jet Patch) | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-03 | 2018-08-28 | 2018-08-29 | 8000
C2012 | Allerdale | Abbeytown to Southfield (Jet Patch) | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-03 | 2018-08-31 | 2018-08-31 | 6000
U2120 | Allerdale | Windergate Road to Bassenthwaite (Jet Patch) | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-03 | 2018-09-05 | 2018-09-07 | 6000
U2117 | Allerdale | Bassenthwaite Village (Jet Patch) | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-01 | 2018-08-03 | 2018-09-04 | 2018-09-04 | 3000
U2137 | Allerdale | Bolton Low Houses (Allerdale Live Data Patches+BH Patching Teams) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-06-01 | 2018-06-18 | 2018-07-02 | 2018-07-13 | 29809.99
Various | Allerdale | Silloth, Maryport, Aspatria, Bridgefoot, Branthwaite, Wigton (Live Data) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-06-01 | 2018-06-18 | 2018-07-16 | 2018-07-20 | 25088.08
C2055 | Allerdale | Caldbeck to Hesket Newmarket | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-08-13 | 2018-08-14 | 2018-08-09 | 2018-08-16 | 10000
C2050 | Allerdale | High Waverbridge to Woodrow | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-01-28 | 2019-02-08 | 2019-01-28 | 2019-02-08 | 20381.28
U2057 | Allerdale | Thornby to Woodhouse (BH Patching Teams) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2018-05-21 | 2018-05-25 | 2018-05-21 | 2018-05-25 | 14000
U2134 | Allerdale | Bolton Wood Lane (BH Patching Teams) | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Patching/Overlays | 3 - High | 2018-05-28 | 2018-06-01 | 2018-05-28 | 2018-06-01 | 10000
C2048 | Allerdale | Sandy Brow to Carwath (BH Patching Teams) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-06-04 | 2018-06-08 | 2018-06-04 | 2018-06-08 | 10000
U2066 | Allerdale | West Woodside, Wigton (BH Patching Teams) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-06-11 | 2018-06-15 | 2018-06-11 | 2018-06-15 | 20000
B5301 | Allerdale | Outgang Road, Aspatria | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-06-18 | 2018-06-22 | 2018-06-18 | 2018-06-22 | 2000
U2156 | Allerdale | Bannest Hill, Hesket Newmarket (BH Patching Teams) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-06-25 | 2018-07-01 | 2018-06-25 | 2018-07-01 | 15000
U2077 | Allerdale | Blennerhasset | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Owerlay | 2 - Medium | 2018-11-01 | 2018-11-30 | 2018-11-26 | 2018-11-30 | 45000
Various | Allerdale | Bothel, Brigham, Pardshaw, Eaglesfield and Lessonhall | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-07-22 | 2019-08-16 | 2019-07-22 | 2019-08-16 | 33826.35
| Allerdale | Staff Time | [8 empty] | 38690.58
| Allerdale | Hilux | [8 empty] | 42015.68
[10 empty] | Total | 850338.89
Barrow
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
Various | Barrow | Purchase of New Plant | Various | NA | NA | NA |  |  |  |  | 42015.68
Various | Barrow | Coring works | Carriageway | NA | Cores | NA |  |  |  |  | 1763.25
Various | Barrow | Staff Time | Various | NA | NA | NA |  |  |  |  | 20719.05
U6021 | Barrow | Sun Street, Ireleth | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 2 - Medium |  |  | 2018-12-05 | 2018-12-13 | 14501.2
U6186 | Barrow | High Street | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High |  |  | 2019-03-11 | 2019-03-15 | 19868.6
U6186 | Barrow | Parker Street | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 2 - Medium |  |  | 2018-07-31 | 2018-08-02 | 16294.9
U6184 | Barrow | Devonshire Road | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High |  |  | 2018-07-30 | 2018-07-30 | 20568
U6156 | Barrow | Risedale Road, Speedhump | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High |  |  | 2018-08-06 | 2018-08-07 | 23650.52
U6127 | Barrow | Dane Ave | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium |  |  | 2018-01-29 | 2018-02-05 | 22423.94
U6163 | Barrow | Moorfield Street | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium |  |  | 2018-10-04 | 2018-10-17 | 30728.23
U6233 | Barrow | Andreas Ave, Walney | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High |  |  | 2018-01-21 | 2018-02-01 | 24135.91
C6009 | Barrow | Yarwell Junction of Ulverston Road, Dalton | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High |  |  | 2018-10-15 | 2018-10-17 | 40076.55
U6199 | Barrow | Greengate Street | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium |  |  | 813/08/2019 | 2019-08-22 | 26375.33
U6205 | Barrow | Church Street | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium |  |  | 2018-01-18 | 2018-01-18 | 20755.62
U6118 | Barrow | Page Bank Lane | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High |  |  | 2018-10-17 | 2018-10-18 | 13298.37
[10 empty] | Total | 337175.15
Carlisle
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
Various | Carlisle | Patching by in-house construction gangs to various identified & prioritised routes Order HCA01779 |  | 2. Permanent Patching by Ops Team | Patching | 3 - High | April | June | 2018-04-16 | 2018-06-29 | 131047.1
Various | Carlisle | Patching by in-house construction gangs to various identified & prioritised routes Order HCA01825 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | june | Aug | 2018-07-02 | 2019-08-31 | 163738.79
U135 | Carlisle | Corporation Road, Carlisle - Contribution to Carlisle City Council Works |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | May | June | 2018-06-23 | 2018-06-23 | 4188.1
C1007 | Carlisle | Sandysike | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | December | December | 2018-11-26 | 2018-11-26 | 14565.94
U1031 | Carlisle | Park Nook (West Hall) | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-03-01 | 2018-03-01 | 2018-03-12 | 2018-03-16 | 22668.62
| Carlisle | Knowewfeild Ave / Belah (Gordon Graham) | Carriageway | 4. Treatment using Rhinopatch or Similar | Jointsealing | 3 - High | September | October | 2018-09-17 | 2019-10-26 | 31997.38
Various | Carlisle | Velocity Patching | Carriageway | 4. Treatment using Rhinopatch or Similar | Jetpatcher | 3 - High | june | june | 2018-07-16 | 2018-07-30 | 20411.7
C2042 | Carlisle | Kirkandrews (West) 480-3725 | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | june | june | 2018-06-18 | 2018-06-23 | 16441.34
| Carlisle | Grearshill Road | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | january | January | 2018-01-28 | 2019-01-30 | 28128.66
| Carlisle | 2017-18 Traffic Management Costs R/Safe | Carriageway | Pot Hole Repairs | Pothole Repairs | 3 - High | September | ocyober | 2018-09-17 | 2019-10-26 | 5170
A7 | Carlisle | Contribution to Story Homes on Greymoorhill | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | May | May | 2018-05-14 | 2018-05-14 | 14074.7
| Carlisle | Cliff Cottages (HCA01877) | Footway | 2. Permanent Patching by Ops Team | Kerbing | 3 - High | 2018-12-01 | 2018-12-01 | 2018-11-26 | 2018-11-26 | 8826.47
| Carlisle | HCA01761 Top Soil Costs | Carriageway | 2. Permanent Patching by Ops Team | Resurfacing | 3 - High | Aug | Aug | 2018-07-02 | 2019-08-31 | 60
| Carlisle | HCA01854 Jet Patching Various Carlisle | Carriageway | 2. Permanent Patching by Ops Team | Resurfacing | 3 - High | Aug | Aug | 2018-04-23 | 2019-08-31 | 2986.91
| Carlisle | HCA01978 Patching January | Carriageway | 2. Permanent Patching by Ops Team | Resurfacing | 3 - High | january | March | 2019-01-07 | 2019-03-31 | 73433.04
| Carlisle | The Flatt (Hanson) | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | April | April | 2018-04-23 | 2018-04-27 | 23557.32
| Carlisle | Plant Costs | [8 empty] | 42015.68
| Carlisle | Temp Traffic Management from 17/18 | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | N/A | 3 - High | April | April |  |  | 430
| Carlisle | A Plant Road Closures |  |  |  |  | April | April |  |  | 3976.5
| Carlisle | Staff Time | [8 empty] | 90943.64
[10 empty] | Total | 698661.89
Copeland
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
U4417 | Copeland | Birks Road, Cleator Moor | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-07-30 | 2018-08-10 | 2018-09-17 | 2018-10-03 | 30000
U4228 | Copeland | Quality Corner, Moresby | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-01-07 | 2019-01-11 | 2019-01-07 | 2019-01-11 | 13994.04
C4015 | Copeland | Bookwell to Queens Drive | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-10-22 | 2019-10-26 | 2019-10-22 | 2019-10-26 | 31850.81
U4228 | Copeland | Brierley Rd, Cleator Moor | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-01-11 | 2019-01-16 | 2018-08-31 | 2018-08-31 | 4878.54
U4230 | Copeland | Jack Trees to Melbreak Ave | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-01-01 | 2019-01-01 | 2019-01-07 | 2019-01-09 | 5327.08
U4224 | Copeland | Priory Drv, Cleator Moor | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-12-12 | 2018-12-18 | 2018-12-10 | 2018-12-14 | 12878.06
U4259 | Copeland | Smithfield Rd & Croadalla Ave, Egremont | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-07-16 | 2018-07-27 | 2018-07-16 | 2018-07-25 | 19007.89
U4026 | Copeland | Lamplugh School to Kirkland | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2018-08-31 | 2018-09-07 | 2018-08-28 | 2018-08-31 | 14526.73
U4388 | Copeland | Balmoral Road | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-02-01 | 2019-02-01 | 2019-02-18 | 2019-02-19 | 4638.79
U4340/ U4339 | Copeland | Ravenhill Road/ Solway View, Kells | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-09-01 | 2018-09-01 | 2018-09-19 | 2018-09-19 | 13073.82
U4341 | Copeland | Saltom Road, Kells | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-09-01 | 2018-09-01 | 2018-09-27 | 2018-09-28 | 7000.02
U4349 | Copeland | North Row Kells, Continued | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2019-02-01 | 2019-02-01 | 2019-02-26 | 2019-02-27 | 4722.7
U4298 | Copeland | Oak Bank, Victoria Road, Whitehaven | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2018-08-01 | 2018-08-01 | 2019-08-28 | 2019-08-29 | 2232.68
C4034 | Copeland | High Road, Kells | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-02-01 | 2019-02-01 | 2019-01-28 | 2019-03-01 | 6810.533
C4034 | Copeland | Ginns to Kells | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2019-02-01 | 2019-02-01 | 2018-11-28 | 2018-11-30 | 8116.14
C4107 | Copeland | Hazleholme, Wath Brow | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-11-21 | 2018-11-21 | 2018-11-21 | 2018-11-23 | 504.71
A5086 | Copeland | A5086 Lamplugh | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-04 | 2500
B5345 | Copeland | Abbey Vale, St Bees | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-02-18 | 2019-02-22 | 2019-02-18 | 2019-02-22 | 65000
Various | Copeland | Velocity Jet Patching | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 2 - Medium | 2018-08-06 | 2018-08-17 | 2018-08-06 | 2018-08-17 | 36722.44
Various | Copeland | Various Pothole Repairs - Cold Fell, Mirehouse and Kells | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2018-11-19 | 2019-02-01 | 2018-05-21 | 2018-06-15 | 49685.25
| Copeland | Hallthwaites | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Pothole Repairs | 3 - High | 2019-11-28 | 2019-12-04 | 2019-11-28 | 2019-12-04 | 15253.8
| Copeland | Staff Time |  |  | Pothole Repairs | [5 empty] | 37355.12
| Copeland | Hilux |  |  | Pothole Repairs | [5 empty] | 42015.68
[10 empty] | Total | 428094.833
Eden
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date |  |  |  | Comments
Various | Eden | April/May Hotbox Order HED02325 & HED02326 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st April 2018 | 31st May 2018 | 1st April 2018 | 31st May 2018 | 100849.03
B5288 | Eden | B5288 Norfolk Road, Penrith |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 19th February 2018 | 24th February 2018 | 19th February 2018 | 24th February 2018 | 6944.56 | Remainder Of Vaule Not Paid In 2017/18 Which Should Have Been Allocated agasint The Pothole Fund
Various | Eden | Eden Area Jet Patcher - July |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 2nd July 2918 | 13th July 2018 | 2nd July 2018 | 13th July 2018 | 21544.06 | As Per Commitment Form (So Includes Traffic Management & Staff Cost Allowance)
Various | Eden | July Hotbox (2No) Order HED02463 & HED02464 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st July 2018 | 31st July 2018 | 1st July 2018 | 31st July 2018 | 45747.97 | As Per Commitment Form (So Includes Staff Cost Allowance)
U3422 | Eden | U3422 Faraday Road, Kirkby Stephen |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 21st November 2018 | 3rd December 2018 | 2018-11-21 | 2019-12-18 | 100813.39 | As Per Commitment Form (So Includes Staff Cost Allowance)
U3426 | Eden | U3426 Westgarth Road, Kirkby Stephen |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 21st November 2018 | 3rd December 2018 | 2018-11-21 | 2019-12-18
U3422 | Eden | U3422 Brougham Lane, Kirkby Stephen |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 21st November 2018 | 3rd December 2018 | 2018-11-21 | 2018-12-18
Various | Eden | August Hotbox (2No) Order HED02492 & HED02493 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st August 2018 | 31st August 2018 | 1st August 2018 | 31st August 2018 | 34089.44 | As Per Commitment Form (So Includes Staff Cost Allowance)
C3005/C3004 | Eden | Patching - Renwick To Melmerby Via Unthank & Gamblesby (Order No: HED02501) |  | 2. Permanent Patching by Ops Team | Patching | 3 - High | 9th August 2018 | 14th September 2018 | 9th August 2018 | 5th September 18 | 37207.86 | Not final costs 17.10.18
Various | Eden | Eden Area Jet Patcher - August |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 13th August 2018 | 31st August 2018 | 13th August 2018 | 31st August 2018 | 28128 | As Per Commitment Form (So Includes Traffic Management & Staff Cost Allowance)
Various | Eden | September Hotbox Order HED02522 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st September 2018 | 30th September 2018 | 1st September 2018 | 30th September 2018 | 11906.05
Various | Eden | October Hotbox Order HED02550 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st October 2018 | 31st October 2018 | 1st October 2018 | 31st October 2018 | 24928.64
Various | Eden | CCC Plant Costs | [8 empty] | 42015.68
A686 | Eden | Meathaw Hill (17/18 works) (Hanson) |  | 1. Surfacing Frameworks - Larger Inlays/Overlays |  | 3 - High |  |  |  |  | 180099.74 | Works carried out in 17/18
A686 | Eden | Meathaw Hill (17/18 works) (Order HED02306) |  | 2. Permanent Patching by Ops Team |  | 3 - High | 30th May 18 | 4th June 18 | 3rd May 18 | 4th May 18 | 10847.18
Various | Eden | TM Velocity Order HED02414 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team |  | 3 - High | 2nd June 18 | 17th June 18 | 2nd June 18 | 17th June 18 | 3246.84
Various | Eden | Eden Area Jet Patcher - September |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team |  | 3 - High | 17th September 2018 | 29th September 2018 | 21st September 2018 | 4th October 2018 | 21761.51 | As Per Commitment Form (So Includes Staff Cost Allowance)
A686 | Eden | Meathaw Hill (Remainder Of Final Account Agreed 24.10.18) (Hanson) |  | 1. Surfacing Frameworks - Larger Inlays/Overlays |  | 3 - High |  |  |  |  | 28668.42 | Remainder Of Final Account Agreed 24.10.2018
Various | Eden | November Hotbox Order HED02584 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st November 2018 | 30th November 2018 | 1st November 2018 | 30th November 2018 | 15868.81 | As Per Commitment Form (So Includes Staff Cost Allowance)
Various | Eden | December Hotbox (2No) Order HED02605 & HED02609 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st December 2018 | 31st December 2018 | 1st December 2018 | 31st December 2018 | 51644.44 | As Per Commitment Form (So Includes Staff Cost Allowance)
Various | Eden | Maulds Meaburn, Askham, Glassonby, Penruddock School |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 10th January 2019 | 17th January 2019 | 10th January 2019 | 20th February 2019 | 80192.55
Various | Eden | Fell Lane/Milner Mount Penrith (HED02418) |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 21st June 18 | 27th June 18 | 21st June 18 | 27th June 1 | 17648.38
Various | Eden | Appleby to Murton (HED02500) |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 6th September 18 | 28th September 18 | 6th September 18 | 1st October 18 | 29945.35
Various | Eden | Wetheriggs Estate (HED02397) |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 31st May 18 | 1st June 18 | 31st May 18 | 1st June 18 | 4895.57
Various | Eden | January Hotbox (2No) Order HED02647 & HED02648 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st January 2019 | 31st January 2019 | 1st January 2019 | 31st January 2019 | 47369.29 | As Per Commitment Form (So Includes Staff Cost Allowance)
Various | Eden | February Hotbox (2No) Order HED02669 & HED02670 |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st February 2019 | 28th February 2019 | 1st February 2019 | 28th February 2019 | 27165.23 | As Per Commitment Form (So Includes Staff Cost Allowance)
Various | Eden | March Hotbox (HED02686) |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 1st March 19 | 31st March 2019 | 1st March 2019 | 31st March 2019 | 4668.74
Various | Eden | Technical Staff Time | [8 empty] | 35010.67
Various | Eden | Advertising Costs | [8 empty] | 276.25
[10 empty] | Total | 1013483.65
South Lakes
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date |  |  |  | Comments
Various | South Lakes | Stainton PC Pothole Patching 2018/19 |  | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2018-05-01 | 2018-05-30 | 2018-05-01 | 2018-05-30 | 8346.51
A593 | South Lakes | Bracelett Hall (East of Broughton-in-FurnessO |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-04-01 | 2018-04-01 | 19th April | 19th April | 33439.28
C5075 | South Lakes | Carex Farm, Crosscrake Church and A65 Stanley Bridge |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-05-01 | 2018-05-01 | 8th and 11th May 2018 | 8th and 11th May 2018 | 17055.9
C5094 | South Lakes | Gatebeck Lane Endmoor |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-05-01 | 2018-05-01 | 17th May | 17th May | 26281.96
U5760 | South Lakes | Biskey Howe Road Bowness |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-06-01 | 2018-06-01 | 8th June | 8th June | 38202.92
U831 | South Lakes | Parkside Road Kendal |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-06-01 | 2018-06-01 | 21st June | 21st June | 30249.89
Various | South Lakes | Pothole Patching 2018/19- Sedgwick PC (c/way patching) |  | 2. Permanent Patching by Ops Team | Patching | 3 - High | 1st June 2018 | 29th June 2018 | 1st June 2018 | 29th June 2018 | 24061.81
U5647 | South Lakes | Pothole patching 2018/19- Homescales Cottages, Old Hutton PC (c/way patching) |  | 2. Permanent Patching by Ops Team | Patching | 3 - High | 1st June 2018 | 22nd June 2018 | 1st June 2018 | 22nd June 2018 | 1856.85
Various | South Lakes | Old Hutton PC- Velocity Patching |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 18th June 2018 | 9th July 2018 | 18th June 2018 | 9th July 2018 | 11714.52
U5602 | South Lakes | Johnscales Farm to Howe Lodge Farm, Lyth - Velocity Patching |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 18th June 2018 | 9th July 2018 | 18th June 2018 | 9th July 2018 | 9982.62
U5419 and C5091 | South Lakes | Dukes Bridge to Ellers Farm and A65 to Lupton Beck |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-08-20 | 2018-08-21 | 2018-08-20 | 2018-08-21 | 38195.42
A5087, U5714, | South Lakes | Roosbeck, Market Street, Broadgate and Swan lane Grasmere |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-08-02 | 2018-08-24 | 2018-08-02 | 2018-08-24 | 150327.51
U5607 | South Lakes | Whetstone Lane, Kendal- Velocity Patching |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 2018-09-03 | 2018-09-21 | 2018-09-03 | 2018-09-21 | 3153.01
U5273 | South Lakes | Gurnal Bridge Lane to A6, Garth Row - Velocity Patching |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 2018-09-03 | 2018-09-21 | 2018-09-03 | 2018-09-21 | 11880.63
U5413 | South Lakes | Puddlemire / Newbiggin Lane, Lupton |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 2018-09-03 | 2018-09-21 | 2018-09-03 | 2018-09-21 | 2770.56
U889 | South Lakes | Vicarage Drive Kendal |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-09-19 | 2019-08-19 | 2018-09-19 | 2018-08-19 | 38224
U5241 | South Lakes | Tow Top Road, High Newton |  | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 2018-09-17 | 2018-09-21 | 2018-09-17 | 2018-09-21 | 1087.17
U5665 | South Lakes | Kentsford Road Grange |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 15177.48
U5760 | South Lakes | Biskey Howe Road Ph2 |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3- High | 2018-12-14 | 2018-12-14 | 2018-12-14 | 2018-12-14 | 37298.45
| South Lakes | Staff | [8 empty] | 108049.67
| South Lakes | Hilux Vehicles | [8 empty] | 42015.68
| South Lakes | Retentions/previous years tickets |  |  | Pothole Repairs | [5 empty] | 17675.35
| South Lakes | New Street |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-12-01 | 2018-12-01 | 2018-12-01 | 2018-12-01 | 16502.29
| South Lakes | Elterwater |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 8540.12
| South Lakes | Brigsteer |  | 1. Surfacing Frameworks - Larger Inlays/Overlays | Patching | 3 - High | 2018-08-01 | 2018-08-01 | 2018-08-01 | 2018-08-01 | 30207.36
| South Lakes | Main Street KL |  | 2. Permanent Patching by Ops Team | Pothole repairs | 3 - High | 2018-12-01 | 2018-12-01 | 2018-12-01 | 2018-12-01 | 639.79
| South Lakes | Beech Hill |  | 2. Permanent Patching by Ops Team | Pothole repairs | 3 - High | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 8642.45
[10 empty] | Total | 731579.2

## Summary
Total Costs of all 6 Areas
Allerdale | 850338.89
Barrow | 337175.15
Carlisle | 698661.89
Copeland | 428094.833
Eden | 1013483.65
South Lakes | 731579.2
Total | 4059333.613

## Drop Down Lists (hidden)
District | Agreed Suitable Treatment | Scheme Type | Priority
Allerdale | 1. Surfacing Frameworks - Larger Inlays/Overlays | Pothole Repairs | 1 - Low
Barrow | 2. Permanent Patching by Ops Team | Resurfacing | 2 - Medium
Carlisle | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Patching | 3 - High
Copeland | 4. Treatment using Rhinopatch or Similar
Eden | 5. Agreed not a prioirty but considered for future Programme/Inspection
South Lakes