## 19-20 Pothole Fund Action Plan
Pot Hole Action Fund report
Schemes to be delivered in 2019 / 20 using the pot hole action funding
ALLERDALE
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
U2306 | Allerdale | Cape Road, Seaton | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-08-01 | 2019-09-01 | 27.08.2019 | 2019-09-03 | 7782.05
U2332 | Allerdale | Joseph Noble Road, Lillyhall | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-08-01 | 2019-09-01 | 12.08.2019 | 2019-08-23 | 25507.86
U2306 | Allerdale | Ling Road, Seaton | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-09-01 | 2019-09-01 | 2019-09-03 | 2019-09-09 | 8044.59
U2188 | Allerdale | Windmill Lane Cockermouth | Carriageway | 2. Permanent Patching by Ops Team | Resurfacing | 3 - High | 2019-06-01 | 2019-06-01 | 2019-06-12 | 2019-06-12 | 22906.8
U2404 | Allerdale | Simonscales Lane, Cockermouth | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-09-01 | 2019-09-01 | 2019-09-12 | 2019-09-23 | 15462.87
B5302 | Allerdale | Waverbridge | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-09-01 | 2019-09-01 | 2019-10-21 | 2019-10-30 | 21365.4
C2014 | Allerdale | Aldoth | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-06-01 | 2019-06-01 | 2019-06-10 | 2019-06-11 | 5905.98
U2939 | Allerdale | The Mount Papcaslte | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-07-01 | 2019-07-01 | 2019-07-22 | 2019-08-02 | 17539.25
U2021 | Allerdale | Saltcoates | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-07-01 | 2019-07-01 | 2019-06-24 | 2019-06-28 | 11619.03
U2783/U2845/U2860 | Allerdale | Gavel Street, Windermere Avenue and Sandy Lonning | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-09-01 | 2019-09-01 | 2019-09-16 | 2019-09-23 | 14911.51
| Allerdale | Cars Mill | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Patching | 3 - High | 2019-05-01 | 2019-05-01 | 2019-05-13 | 2019-09-13 | 27000
| Allerdale | Silloth to Westnewton | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-09-01 | 2019-09-01 | 2019-09-16 | 2019-09-30 | 274857
| Allerdale | Syke Road, Wigton | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2020-03-01 | 2020-03-01 | 2020-03-03 | 2020-03-20 | 26610.99
| Allerdale | Station Road, Wigton | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2020-01-01 | 2020-01-01 | 2020-01-22 | 2020-01-24 | 8657.39
| Allerdale | B5302 Waverbridge | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-10-01 | 2019-10-01 | 2019-10-21 | 2019-10-30 | 21365.4
| Allerdale | Moorclose Shops | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Patching | 2 - Medium | 2019-10-21 | 2019-10-23 | 2019-10-21 | 2019-10-23 | 16992.99
|  | Staff Time | [8 empty] | 34792.78
[10 empty] | Total | 561321.89
BARROW
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
C6010 | Barrow | ABBEY RD - HBA06079 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2020-01-01 |  | 2020-01-20 | 2020-01-21 | 4566.14
U6171 | Barrow | WORDSWORTH ST - HBA06085 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-11-01 |  | 2019-11-26 | 2019-11-28 | 13507.86
U6211 | Barrow | ARGYLE ST - HBA06082 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-11-01 |  | 2019-11-29 | 2019-12-04 | 6217.17
U6086 | Barrow | Woodward Ave - HBA06089 | Carriageway | 2. Permanent Patching by Ops Team | Resurfacing | 3 - High | 2020-01-01 |  | 2020-01-08 | 2020-01-15 | 11478.13
U6157 | Barrow | Tanterbank, Dalton - HBA06083 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-12-01 |  | 2019-12-05 | 2020-01-10 | 39394.91
|  | Staff Time | [8 empty] | 18708.58
[10 empty] | Total | 93872.79
CARLISLE
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
| Carlisle | Retention Costs from 18/19 Schemes (Kirkandrews, Grearshill & Sandysike) | [8 empty] | 630.76
Various | Carlisle | Dalston Village lay-by, next to cumberland - Dalston PC EP00339593 | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Patching | 3 - High | 2019-08-01 | 2019-08-01 | 2019-08-01 | 2019-08-01 | 1875.66
C1007 | Carlisle | Highwood Crescent Carlisle HCA02245 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-12-01 | 2019-12-01 | 2019-12-12 | 2019-12-13 | 3654.14
C2042 | Carlisle | Gilsland junction from Bridge pub to Northumberland boundry. | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing using micro asphalt | 3 - High | 2019-08-01 | 2019-08-01 | 2019-08-28 | 2019-08-28 | 2485
| Carlisle | Tarmac Corby Hill | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2019-09-01 | 2019-09-01 | 2019-09-16 | 2019-09-16 | 9855.96
| Carlisle | Pre Surface Dressing Patching October (HCA02198) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | October | October | 2019-10-01 | 2019-10-31 | 52820.67
| Carlisle | Pothole Patching November (HCA02216) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | November | November | 2019-11-01 | 2019-11-30 | 74014.11
Various | Carlisle | Pothole Patching December HCA02234 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-12-01 | 2019-12-01 | 2019-12-09 | 2019-12-20 | 48848.86
C1007 | Carlisle | Pothole Patching January (HCA02254) | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | Jan | Jan |  |  | 75356.32
| Carlisle | Heathersgill Pothole Manhole (HCA02244) | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | Jan | Jan |  |  | 731.88
| Carlisle | Staff Time | [8 empty] | 71361.99
[10 empty] | Total | 341635.35
COPELAND
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
C4006 | Copeland | Fire station | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2019-04-01 | 2019-04-02 | 2019-04-01 | 2019-04-02 | 2262.55
U4022 | Copeland | Mill Street, Frizington | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-09-02 | 2019-09-13 | 2019-08-12 | 2019-08-23 | 21323.11
U4018 | Copeland | Lanefoot, Asby | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-09-16 | 2019-09-20 | 2019-09-16 | 2019-10-04 | 24519.54
C4001 | Copeland | Featherknott, Dyonside | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-10-01 | 2019-10-02 | 2019-07-15 | 2019-07-17 | 3469.15
U4009 | Copeland | Howgate to Low Moresby | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 2 - Medium | 2019-09-02 | 2019-09-06 | 2019-09-02 | 2019-09-06 | 9266.23
C4006 | Copeland | Pica to Castlerigg Farm | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2020-01-20 | 2020-02-07 | 2020-01-20 | 2020-02-06 | 30743.6
U4383 | Copeland | Park Drive, Whitehaven | Carriageway | 2. Permanent Patching by Ops Team | Patching | 2 - Medium | 2019-12-16 | 2019-12-17 | 2019-12-16 | 2019-12-17 | 5895.33
|  | Staff Time | [8 empty] | 14385.64
[10 empty] | Total | 111865.15
EDEN | [9 empty] | Budget
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
Various | Eden | Velocity Jet Patcher - Eden Area | Carriageway | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Pothole Repairs | 3 - High | 2019-04-01 | 2019-05-01 | 1st May 2019 | 24th May 2019 | 64760.04
Various | Eden | Permeant Repairs By 4 Operative Team Following Safety Inspection August HED02852 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-08-01 | 2019-08-01 | 2019-08-01 | 2019-08-31 | 15050.65
Various | Eden | Permeant Repairs By 4 Operative Team Following Safety Inspection September HED02895 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-09-01 | 2019-09-01 | 2019-09-01 | 2019-09-30 | 12732.52
Various | Eden | Permeant Repairs By 4 Operative Team Following Safety Inspection October HED02933 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-31 | 13217.67
U3101, U3099, U3100, C3004, C3009 | Eden | Ousby Village Patching HED02929 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-10-01 | 2019-12-01 | 2019-11-19 | 2019-12-03 | 33295.89
C3077/B6276/B6259/A683 | Eden | Tour of Britain Route HED02855 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-08-16 | 2019-09-05 | 2019-08-16 | 2019-09-05 | 41149.79
| Eden | Costs from 18/19 | [8 empty] | 6095.34
Various | Eden | Potholing Team November HED02971 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-11-01 | 2019-11-30 | 2019-11-01 | 2019-11-30 | 37743.26
U3085 | Eden | U3085 Parkhead Renwick HED02974 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-12-09 | 2019-12-12 | 2019-12-09 | 2019-12-12 | 6833
U3174 | Eden | U3174 Whale Askham HED02975 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2020-01-24 | 2020-02-06 | 2020-01-24 | 2020-02-06 | 21457.65
A686 | Eden | A686 Carleton Village Layby HED02980 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-05 | 2732.17
Various | Eden | Potholing Team Dec HED03003 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2019-12-01 | 2019-12-31 | 2019-12-01 | 2019-12-31 | 7382.98
A686 | Eden | A686 Langwathby Bridge HED03011 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2019-12-16 | 2019-12-16 | 2019-12-16 | 2019-12-16 | 3484.23
U3102, C3039 | Eden | U3102 & C3039 Junc between The Wardway Alston HED03013 | Carriageway | 2. Permanent Patching by Ops Team | Patching | 3 - High | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2090.77
Various | Eden | Potholing Team January HED03033 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2020-01-01 | 2020-01-31 | 2020-01-01 | 2020-01-31 | 14312.46
Various | Eden | Potholing Team Feb HED03057 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2020-02-01 | 2020-02-29 | 2020-02-01 | 2020-02-29 | 27707.86
Various | Eden | Potholing Team March HED03086 | Carriageway | 2. Permanent Patching by Ops Team | Pothole Repairs | 3 - High | 2020-03-01 | 2020-03-31 | 2020-03-01 | 2020-03-31 | 24148.12
| Eden | Staff Time | [8 empty] | 16030.35
[10 empty] | Total | 350224.75
SOUTH LAKES
Scheme Name |  |  | Scheme Details | [5 empty] | Actual Works Start Date | Actual Completion Date | Cost to CCC (£)
Road No. | District | Name | Asset Groups | Agreed Suitable Treatement | Scheme Type - eg, pothole repairs, resurfacing, patching | Priority | Estimated Monthly Start Date | Estimated Monthly Completion Date
U5489 | South Lakes | Dowbiggin Lane Sedbergh | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2019-02-01 | 2019-02-01 | 2019-02-15 | 2019-02-15 | 13486.42
U953 | South Lakes | Kent Park Avenue Kendal | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2019-04-01 | 2019-04-01 | 2019-04-04 | 2019-04-04 | 15820.38
A683 | South Lakes | High Barn, | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2019-06-01 | 2019-06-01 | 2020-06-27 | 2020-06-28 | 53142.79
A593 | South Lakes | Troughton West of Torver | Carriageway | 1. Surfacing Frameworks - Larger Inlays/Overlays | Resurfacing | 3 - High | 2019-06-01 | 2019-06-01 | 2019-06-27 | 2019-06-28 | 53672.04
|  | Previous years costs | [8 empty] | 15204.28
|  | Staff Time | [8 empty] | 49069.66
[10 empty] | Total | 200395.57
1659315.5

## Summary
Total Costs of all 6 Areas
Allerdale | 561321.89
Barrow | 93872.79
Carlisle | 341635.35
Copeland | 111865.15
Eden | 350224.75
South Lakes | 200395.57
Total | 1659315.5

## Drop Down Lists (hidden)
District | Agreed Suitable Treatment | Scheme Type | Priority
Allerdale | 1. Surfacing Frameworks - Larger Inlays/Overlays | Pothole Repairs | 1 - Low
Barrow | 2. Permanent Patching by Ops Team | Resurfacing | 2 - Medium
Carlisle | 3. Defects in Rural Areas treated using Jet Patcher or similar by Ops Team | Patching | 3 - High
Copeland | 4. Treatment using Rhinopatch or Similar
Eden | 5. Agreed not a prioirty but considered for future Programme/Inspection
South Lakes